## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | User Story Point | Assignee | Status
1 | 1 | US01 | As a visitor, I should be able to “Register” to the application as a seller/buyer by providing my credentials | MUST HAVE | 5 | 1119547 | 3- Completed
1 | 1 | US02 | As a visitor, I should be able to “Login” to the application as a seller/buyer by providing my credentials | MUST HAVE | 5 | 1119547 | 3- Completed
1 | 1 | US03 | As a visitor, I should be able to deactivate my account | MUST HAVE | 5 | 1119547 | 3- Completed
1 | 1 | US04 | As a Buyer,I should be able to add my products to wishlist/cart | SHOULD HAVE | 5 | 1119547 | 3- Completed
1 | 1 | US05 | As a buyer,I should be able to move my products from wishlist to cart and remove my products from wishlist/cart | SHOULD HAVE | 5 | 1119547 | 3- Completed
1 | 1 | US06 | As a seller, I should be able to add my products , so that the buyers can view my products | SHOULD HAVE | 5 | 1119537 | 3- Completed
1 | 1 | US07 | As a seller,I should be able to update stocks of my product | SHOULD HAVE | 5 | 1119537 | 3- Completed
1 | 1 | US08 | As a seller, I should be able to delete my product, so that it no longer appear to the buyer | SHOULD HAVE | 5 | 1119537 | 3- Completed
1 | 1 | US09 | As a Buyer, I should be able to view the products by product name and category | SHOULD HAVE | 5 | 1119537 | 3- Completed
1 | 1 | US10 | As a Privileged Buyer, I should be able to buy unlimited quantity of a specific product | SHOULD HAVE | 5 | 1119537 | 3- Completed
1 | 1 | US11 | As a Buyer, I should be able to place order on products | SHOULD HAVE | 5 | 1119566 | 3- Completed
1 | 1 | US12 | As a Buyer, I should be able to view my past orders | SHOULD HAVE | 5 | 1119566 | 3- Completed
1 | 1 | US13 | As a buyer, I should be able to reorder the products | SHOULD HAVE | 5 | 1119566 | 3- Completed
1 | 1 | US14 | As a seller, I should be able to view orders placed on their products | SHOULD HAVE | 5 | 1119566 | 3- Completed
1 | 1 | US15 | As a seller, I should be manage the status of the order on my product | SHOULD HAVE | 5 | 1119566 | 3- Completed
Note on F1: Kindly refrain from providing more than 8 points to user stories
Note on F2: Kindly refrain from providing more than 8 points to user stories

## Sprint I Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3
[8 empty] | 54 | 27 | 27 | 0
SPRINT 1 BACKLOG
US-01 | T1 | Install all software and requirements | 2021-06-24 | 2021-06-24 | 1119547 | System Test | 3- Completed | 2 | 2 | 0 | 0
| T2 | Create Spring starter Project for MS | 2021-06-24 | 2021-06-24 |  | Coding | 3- Completed | 0.5 | 0.5 | 0 | 0
| T3 | Implement DTO entity and repo Class | 2021-06-24 | 2021-06-24 |  | Coding | 3- Completed | 1 | 1 | 0 | 0
| T4 | Implement Table scripts | 2021-06-25 | 2021-06-25 |  | Coding | 3- Completed | 1.5 | 1.5 | 0 | 0
| T5 | Implement Service and Controller class | 2021-06-25 | 2021-06-25 |  | Coding | 3- Completed | 7 | 3 | 4 | 0
| T6 | Implement Validator Class | 2021-06-25 | 2021-06-25 |  | Coding | 3- Completed | 2 | 1 | 1 | 0
| T7 | Created and added annotations for Eureka Config Server and Zuul in ms | 2021-06-25 | 2021-06-25 |  | Coding | 3- Completed | 2 | 0 | 2 | 0
| T8 | Checking the end points | 2021-06-25 | 2021-06-25 |  | General | 3- Completed | 2 | 0 | 2 | 0
US-02 | T1 | Install all software and requirements | 2021-06-24 | 2021-06-24 | 1119537 | System Test | 3- Completed | 2 | 2 | 0 | 0
| T2 | Create Spring starter Project for MS | 2021-06-24 | 2021-06-24 |  | Coding | 3- Completed | 0.5 | 0.5 | 0 | 0
| T3 | Implement DTO entity and repo Class | 2021-06-24 | 2021-06-24 |  | Coding | 3- Completed | 1 | 1 | 0 | 0
| T4 | Implement Table scripts | 2021-06-25 | 2021-06-25 |  | Coding | 3- Completed | 1.5 | 1.5 | 0 | 0
| T5 | Implement Service and Controller class | 2021-06-25 | 2021-06-25 |  | Coding | 3- Completed | 8 | 3 | 4 | 0
| T6 | Implement Validator Class | 2021-06-25 | 2021-06-25 |  | Coding | 3- Completed | 1 | 1 | 1 | 0
| T7 | Created and added annotations for Eureka Config Server and Zuul in ms | 2021-06-25 | 2021-06-25 |  | Coding | 3- Completed | 2 | 0 | 2 | 0
| T8 | Checking the end points | 2021-06-29 | 2021-06-25 |  | General | 3- Completed | 2 | 0 | 2 | 0
US-03 | T1 | Install all software and requirements | 2021-06-24 | 2021-06-24 | 1119566 | System Test | 3- Completed | 2 | 2 | 0 | 0
| T2 | Create Spring starter Project for MS | 2021-06-24 | 2021-06-24 |  | Coding | 3- Completed | 0.5 | 0.5 | 0 | 0
| T3 | Implement DTO entity and repo Class | 2021-06-24 | 2021-06-24 |  | Coding | 3- Completed | 1 | 1 | 0 | 0
| T4 | Implement Table scripts | 2021-06-25 | 2021-06-25 |  | Coding | 3- Completed | 1.5 | 1.5 | 0 | 0
| T5 | Implement Service and Controller class | 2021-06-25 | 2021-06-25 |  | Coding | 3- Completed | 8 | 3 | 4 | 0
| T6 | Implement Validator Class | 2021-06-25 | 2021-06-25 |  | Coding | 3- Completed | 1 | 1 | 1 | 0
| T7 | Created and added annotations for Eureka Config Server and Zuul in ms | 2021-06-25 | 2021-06-25 |  | Coding | 3- Completed | 2 | 0 | 2 | 0
| T8 | Checking the end points | 2021-06-25 | 2021-06-25 |  | General | 3- Completed | 2 | 0 | 2 | 0
4
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work

## Sprint II Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3
[8 empty] | 54 | 27 | 27 | 0
SPRINT 2 BACKLOG
US-01 | T1 | AWS Configuration | 28/06/2021 | 29/06/2021 | 1119547 | Build | 2- In Progress | 12 | 7 | 7 | 0
| T2 | Minor Enhancement | 28/06/2021 | 29/06/2021 | 1119547 | Coding | 3- Completed | 6 | 2 | 2 | 0
US-02 | T1 | AWS Configuration | 28/06/2021 | 29/06/2021 | 1119537 | Build | 2- In Progress | 12 | 7 | 7 | 0
| T2 | Minor Enhancement | 28/06/2021 | 29/06/2021 | 1119537 | Coding | 3- Completed | 6 | 2 | 2 | 0
US-03 | T1 | AWS Configuration | 28/06/2021 | 29/06/2021 | 1119566 | Build | 2- In Progress | 12 | 7 | 7 | 0
| T2 | Minor Enhancement | 28/06/2021 | 29/06/2021 | 1119566 | Coding | 3- Completed | 6 | 2 | 2 | 0
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work

## Retrospection
Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
2021-06-24 | 2021-06-25 | All Members | Discussion on function of Microservices | Starting without discussing how it works | Discussion on assigning members for Microservices | Meeting was held for collabration
2021-06-24 | 2021-06-25 | All Members | Establishing efficient communication, Setting per day tasks | Stressing out | Being Proactive,Being Active listners,Being Cordial | Take breaks,Discuss in meeting
2021-06-24 | 2021-06-25 | All Members | Analysing the methods,URL,compatiblity and implementation of MS | Doing any updates/changes without discussion | Checking output as per requirement | Stand up meeting was held
2021-06-24 | 2021-06-25 | All Members | Focussing on tasks and results | Rushing blindly | Being Supportive,Being Organised,Being Productive | Discussion with team mates

## Stand up Meeting
Sprint | US ID | Day | Assigned To | Points Discussed | Impediments | Action Taken
|  | 1 |  | Install dependencies
|  | 1 |  | Plan Userstories
|  | 1 | 1119547 | Update Agile Sheet
1 | 1 2 3 | 1 | 1119566 1119547 1119537 | Implement DTO Entity and repo classes for user ms
1 | 1 2 3 | 2 | 1119566 1119547 1119537 | Implement Service and controller clases for Ordefr ms
1 | 1 2 3 | 3 | 1119566 1119547 1119537 | Add Config Server Eureka and Zuul
1 | 1 2 3 | 4 | 1119566 1119547 1119537 | AWS deployment